## Timeline
|  |  | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | Date
Step | Descripton | Hours planned | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | Week | Current status | Responsible | Responsible II | Responsible III
Projectplan |  | 4 | 2020-05-25: 2; 2020-06-01: 2 |  | done | Timo | Max
Alternatives to CNN | Discover and learn about alternatives to CNN for image processing. | 6 | 2020-05-25: 3; 2020-06-01: 2; 2020-06-08: 1 |  | in progress | John
Dokumention | [11 empty] | in progress
Memo |  | 8 | [9 empty] | in progress | All | bar: 2020-05-25 to 2020-07-13
Github Tutorial |  | 2 | 2020-05-25: 2 |  | done | Max
Coding | [11 empty] | open | Jonas | John | Max | bar: 2020-06-08 to 2020-07-06
Tutorials sichten/erstes Netz |  | 12 | 2020-06-08: 12 |  | open | Jonas | John
Trainigsdaten besorgen |  | 5 | 2020-06-15: 5 |  | in progress | All
Erste Testläufe |  | 10 | 2020-06-15: 10 |  | open
Optimierung(Schichten/Anzahl Neuronen) |  | 24 | 2020-06-22: 12; 2020-06-29: 12 |  | open
Aufbereitung für Abgabe |  | 12 | 2020-07-06: 12 |  | open
Chapter 2 (What is ML?) | [11 empty] | in progress | bar: 2020-06-01 to 2020-06-08
Einleitung |  | 6 | 2020-06-01: 6 |  | in progress | Giulia
Data |  | 12 | 2020-06-01: 6; 2020-06-08: 6 |  | open | Giulia | Timo
Chapter 3 (Classic ML) | [11 empty] | in progress | Timo | bar: 2020-06-08 to 2020-06-22
Einleitung |  | 6 | 2020-06-08: 6 |  | in progress | Timo | Max
Supervised |  | 12 | 2020-06-08: 6; 2020-06-15: 6 |  | open | Timo
Unsupervised | Max hat Interesse an SVM | 24 | 2020-06-15: 12; 2020-06-22: 12 |  | open | Timo | Max
Chapter 4 (Deep learning) | [11 empty] | open | Jonas | John | Max | bar: 2020-06-01 to 2020-06-22
Einleitung |  | 12 | 2020-06-01: 6; 2020-06-08: 6 |  | open
CNN |  | 6 | 2020-06-01: 3; 2020-06-08: 3 |  | open
Other |  | 12 | 2020-06-08: 4; 2020-06-15: 4; 2020-06-22: 4 |  | open
Chapter 5 (Ensemble methods) - optional | [11 empty] | open | All | bar: 2020-06-22 to 2020-06-29
Einleitung |  | 6 | 2020-06-22: 6 |  | open
Weiterführend |  | 6 | 2020-06-29: 6 |  | open
Chapter 6 (Reinforement learning) - optional | [11 empty] | open | All | bar: 2020-06-22 to 2020-06-29
Einleitung |  | 6 | 2020-06-22: 6 |  | open
Weiterführend |  | 6 | 2020-06-29: 6 |  | open
Final Paper | [11 empty] | open | All | bar: 2020-06-29 to 2020-07-13
Wrap up | Alle Arbeitsschritte zusammenfassen und strukturieren. | 30 | 2020-06-29: 10; 2020-07-06: 10; 2020-07-13: 10 |  | open | All
Presentation |  | 45 | 2020-06-29: 10; 2020-07-06: 15; 2020-07-13: 20 |  | open | All
|  | 272 | 8 | 26 | 45 | 38 | 41 | 45 | 38 | 31
All
Jonas
Timo
Max
Giulia
John
open
in progress
done